FORMATIVE ASSESSMENT ACTIVITIES

Unit standard 119671

Activity 1(SO1, AC1) (Group activity)

Once you have managed to secure a contract, whether through a tender or otherwise, you have to study the contract in detail.  In a group, discuss why a contract should be studied in detail.

Activity 2: (SO1, AC1-3) (Group activity)

- In handout 1 you will find an example of a contract.  In a group, study the contract and do the following: Prioritise the tasks

- Identify completion dates

- Allocate resources

- Write down the criteria for the tasks

- Identify the risks to your business and state how you will prevent unforeseen circumstances from putting your business at risk.

- Complete the contract action plan on the next page

| CONTRACT ACTION PLAN |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task list | Completion Date | Who will be responsible | Resources | Criteria | Risks | How prevented |

Activity 3 (SO2, AC1-2) (Group activity)

- In a group, do a risk assessment of at least three risks identified in the previous exercise.  Use the table on the next page as a guideline.

- Then draw up a plan to control the risks.  Use the table on the next page as a guideline

Activity 4: (SO2, AC3) (Group activity)

In a group, study the contract to find out which documents have to be sent with the invoice in order for payment to be made.

| RISK ASSESSMENT |  |  |
| --- | --- | --- |
| Identify uncertainties / risks Explore the entire contract and look for areas of uncertainty. | Analyse risks Specify how those areas of uncertainty can impact on delivering the products or service as required by the contract | Prioritise risks - Which risks should be eliminated completely, because they have the potential of impacting extremely on the business or because they will need regular management attention, - And which risks are small enough not to impact too much on the business and will not need detailed management attention |

| RISK CONTROL |  |  |  |
| --- | --- | --- | --- |
| The nature of the risk | How will the risk be spotted | What must be done to resolve it | Who will do it (be accountable for recovery from the risk) |

Activity 5(SO2, AC3-4) (Group activity)

In a group, draw up an events control chart.  Use the contract action plan as an example.  Remember to state how you will monitor progress

| Event . | Scheduled date | Anticipated date | Achieved date | Monitor progress | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 sign off layout plan | 7.2.2008 | 26.2.2008 | 15.3.2008 | Contact decision makers weekly | Signing off a layout plan for new offices delayed because of inability to get the decision makers together |

Activity 6 (SO3, AC1, 2, 4) (Group activity)

The contract in handout 1 has a detailed dispute management procedure.  In a group, study the procedure and summarise the mediation in non-urgent matters procedure, specifically the following points:

- Written notification of a dispute

- Payment of costs

- When can the operator declare a dispute

- What happens if a settlement cannot be reached within 60 days

- If a settlement is reached, who must record the settlement

- Who must establish and regulate procedures for the mediation

Activity 7 Conflict (Individual activity)

- Name and explain the three outcomes of conflict.  (6)

- List the steps involved in managing conflict or disagreement.  (6)

Activity 8: Communication (Individual activity)

- What are the responsibilities of the sender of the message?

- What are the responsibilities of the receiver of the message?

- Why is feedback so important to good communication?

- List six things you can do to improve your communication skills.  (6)

Activity 9: (SO3, AC3, 4) Group activity

- You have been informed by the union that a general strike is going to start in 5 days. Prepare for negotiating with the Employer to use a substitute operator.

- Negotiate with one of the other groups acting as the employer.  Once agreement has been reached, note which documents have to be completed to formalise this change.

Activity 10: (SO4, AC1-2, 4) (Group Activity)

In a group, draw up a form to write a report about the contract once it has finished.  In the appropriate place, write the details you have available, such as resources, the schedule, etc.  Remember to include the following:

- A description of the overall progress of the contract,

- Resources used,

- Costs incurred

- And the schedule followed.

- An analysis of the problems encountered,

- How these issues were approached or handled,

- Whether they worked,

- And what, if any, changes were made to the project schedule as a result of these pressures.

### REPORT

- In a group, develop a sign off form to attach to the report.

- List three problems that can occur during the close-out of a contract.

- What should be done to ensure that a contract is closed out?

Activity 11: (SO4, AC3) (Group activity)

In a group, draw up a questionnaire to use when doing an audit about the success of the contract.  Remember to include:

- Was the contract on schedule as initially laid out?

- Was the contract within budget?

- Was the contract on time?

- Did the completed contract meet the goal or objectives set out?

- Was monitoring adequate?

- What were the issues or problems encountered?

- What action was taken to correct this issue or issues?

- Was the solution or corrective action or actions effective?

- What can be learned from this event for future reference?

- Responsibilities,

- Helpful conditions they identified during their involvement with the contract

- Unhelpful conditions or hindrances they encountered in completing their tasks, and

- Suggestions for dealing with these difficulties and the contract as a whole.